## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
05p5ePcU2kWSDU_rlobAJMkAJjSN | Define non-functional requirements | Analysis/Software requirements | Completed | Important | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 01/01/2025 | 02/28/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Red
0cilRbio-EKnrQw4_GeY3ckABYZU | Implement Stock forecasting using ARIMA, Prophet, and LSTM | Development | Completed | Important | Amangilihewa V.S.D it21318184 | Tharana P.A.S it21822094 | 10/31/2025 | 05/01/2025 | 07/31/2025 | false | false | 10/31/2025 | Amangilihewa V.S.D it21318184 |  |  | Red
1Pr2SaNn7064TIqX8ZLsIskAKh3j | Develop Fire Detection model (YOLOv8m) and integrate IoT hardware | Development | Completed | Important | Tharana P.A.S it21822094 | Tharana P.A.S it21822094 | 10/31/2025 | 05/01/2025 | 07/31/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Red
2mw4jm9PkkOED4oDUQEbdskALX36 | Analyze warehouse inefficiencies, fire hazards, space use, and predictive gaps | Design | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 03/01/2025 | 04/30/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
3CMVoI4gJkqXLPtlqSdvM8kAD3xo | Prepare final presentation and project report | Pilot & Deployment | Completed | Important | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 09/10/2025 | 10/31/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Red
3EfavdJY6k6b8vMrnl2OTckALYmj | Design Predictive Analytics models | Design | Completed | Important | Amangilihewa V.S.D it21318184 | Tharana P.A.S it21822094 | 10/31/2025 | 03/01/2025 | 03/31/2025 | false | false | 10/31/2025 | Amangilihewa V.S.D it21318184 |  |  | Red
5LiIz_hgAUmzLddGA9CalskAF921 | Integrate all modules using MERN + Flask architecture | Development | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 05/01/2025 | 07/31/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
8fmWIZk1OUegSgWDoW0fx8kAHDtW | Design unified MERN + Flask architecture and dashboard layout | Design | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 03/01/2025 | 04/30/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
B9YcvNiLJk-HSGqAP0VZBckAIcPO | Perform feasibility analysis and system flow analysis | Analysis/Software requirements | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 01/01/2025 | 02/28/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
EPfDGoaKsECI-i3Pjoz_wckAG2Bx | Design MongoDB schema for each module (routes, fire logs, stock data, space data) | Design | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 03/01/2025 | 03/31/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
HrOHtZEws06X2VQQcI4Uy8kALYgp | Specify hardware requirements | Analysis/Software requirements | Completed | Medium | Tharana P.A.S it21822094 | Tharana P.A.S it21822094 | 10/31/2025 | 01/01/2025 | 02/28/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
Iw5IgwAzqkGz6HvD3AbZPckAOP9A | Design Space Optimization | Design | Completed | Important | Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 03/01/2025 | 04/30/2025 | false | false | 10/31/2025 | Abeydeera A.A.A.S it21822780 |  |  | Red
LXCrnWCw00OZ_09LzQF9B8kAD95K | Analyze warehouse inefficiencies, fire hazards, space use, and predictive gaps | Analysis/Software requirements | Completed | Important | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 01/01/2025 | 02/28/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Red
Pa8yWb27NkKpWTa-QboUwckAGimK | Integrate routing, fire, stock, and space modules into single dashboard | Development | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 05/01/2025 | 07/31/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
RX1S52L-T0Kk3Hw0eXQdK8kAGMGq | Prepare documentation and commercialization analysis | Pilot & Deployment | Completed | Important | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 09/10/2025 | 10/31/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Red
Rkx4yaDUREKYPVcl4NyW7ckAOtDX | Validate stock anomaly and worker classification outputs | Testing | Completed | Medium | Amangilihewa V.S.D it21318184 | Tharana P.A.S it21822094 | 10/31/2025 | 08/01/2025 | 09/10/2025 | false | false | 10/31/2025 | Amangilihewa V.S.D it21318184 |  |  | Green
RrYK0Q-SykmvDAgVJP1-MckAGB5_ | Test IoT alert accuracy | Testing | Completed | Medium | Tharana P.A.S it21822094 | Tharana P.A.S it21822094 | 10/31/2025 | 08/01/2025 | 09/10/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
Sz_Xn9Sr5k2YH43RxRU728kAO2U5 | Define functional requirements for each module | Analysis/Software requirements | Completed | Important | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 01/01/2025 | 02/28/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Red
Vw1hztEMbU-sAaRO7wUpg8kAJN-S | Identify hardware, software, and IoT integration boundaries | Scope | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/30/2025 | 12/10/2024 | 11/30/2025 | false | false | 10/30/2025 | Tharana P.A.S it21822094 |  |  | Green
_bCzfvSLf0On50LIo8Rtj8kAFWuW | Define project goal: “Optimized Warehouse Management System leveraging Industry 4.0 technologies” | Scope | Completed | Important | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/30/2025 | 12/01/2024 | 12/20/2024 | false | false | 10/30/2025 | Tharana P.A.S it21822094 |  |  | Red
bRgiSBfs7k2GXeWH3SzEjskAIUZG | Analyze dataset needs (fire/shelf images, stock logs, worker logs, warehouse map) | Analysis/Software requirements | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094 | Tharana P.A.S it21822094 | 10/31/2025 | 01/01/2025 | 02/28/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
bdjNIvfazUmuW3HApqPSoMkALSih | Test UI responsiveness and data synchronization | Testing | Completed | Medium | Palihena P.D.M.P it21079672 | Tharana P.A.S it21822094 | 10/31/2025 | 08/01/2025 | 09/10/2025 | false | false | 10/31/2025 | Palihena P.D.M.P it21079672 |  |  | Green
c7uFG_MPKEGtI5Z6o6U4hskAEuuE | Conduct integration testing | Testing | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 08/01/2025 | 09/10/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
fCR7UPIFpkyG4rZ84LuRJskAGaLz | Outline commercial goals and target market scope | Scope | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/30/2025 | 12/01/2024 | 12/31/2024 | false | false | 10/30/2025 | Tharana P.A.S it21822094 |  |  | Green
hdm8iXspVkqCUtxYNUftFskALET2 | Define main and specific objectives for each module | Scope | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/30/2025 | 12/10/2024 | 12/20/2024 | false | false | 10/30/2025 | Tharana P.A.S it21822094 |  |  | Green
lUkFAXC0AUuZAdcGFgK_EMkADxTb | Develop Worker performance classifier using Gradient Boosting / Random Forest | Development | Completed | Important | Amangilihewa V.S.D it21318184 | Tharana P.A.S it21822094 | 10/31/2025 | 05/01/2025 | 07/31/2025 | false | false | 10/31/2025 | Amangilihewa V.S.D it21318184 |  |  | Red
l_QZlTqr2kOWDBwyFEw5-skAHAy8 | Identify 4 main modules: Route Optimization, Fire Detection, Stock Monitoring, Space Optimization | Scope | Completed | Important | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/30/2025 | 12/01/2024 | 12/10/2024 | false | false | 10/30/2025 | Tharana P.A.S it21822094 |  |  | Red
mHSvWmDXAEy95iwPfskxI8kAIMS_ | Identify existing challenges and research gaps from literature | Analysis/Software requirements | Completed | Important | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 01/01/2025 | 02/28/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Red
n3d7Cwpv70mdeCrbgDBdGskAB2a9 | Validate space utilization improvements | Testing | Completed | Medium | Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 08/01/2025 | 09/10/2025 | false | false | 10/31/2025 | Abeydeera A.A.A.S it21822780 |  |  | Green
o7NLuvFgpEmEeOOdqNEDSckAKnga | Implement Space Optimization with 3D visualization (Best-Fit bin-packing) | Development | Completed | Important | Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 05/01/2025 | 07/31/2025 | false | false | 10/31/2025 | Abeydeera A.A.A.S it21822780 |  |  | Red
rFgp4SiQUkuzK6g_IzOLzskAEmva | Select technology stac | Analysis/Software requirements | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 01/01/2025 | 02/28/2025 | false | false | 10/31/2025 | Palihena P.D.M.P it21079672 |  |  | Green
rUlHfHn_TUyV3BQ4BsWl08kABM4m | Design database schema (MongoDB) and API intercommunication | Development | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 05/01/2025 | 07/31/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
uSxsFppOxkeYoZ6uPm0QqskAKqay | Design Fire Detection & IoT Alert subsystem | Design | Completed | Important | Tharana P.A.S it21822094 | Tharana P.A.S it21822094 | 10/31/2025 | 03/01/2025 | 04/30/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
vCEa4PqhhU28g5xNoHmJ68kAOnGO | Design Route Optimization algorithm (TSP + A)* | Design | Completed | Important | Palihena P.D.M.P it21079672 | Tharana P.A.S it21822094 | 10/31/2025 | 03/01/2025 | 04/30/2025 | false | false | 10/31/2025 | Palihena P.D.M.P it21079672 |  |  | Red
w7OOaLKyWE608FWemg7ofMkAL9qe | Perform unit testing for all modules (TSP, YOLO, ML models, 3D) | Testing | Completed | Medium | Amangilihewa V.S.D it21318184;Tharana P.A.S it21822094;Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 08/01/2025 | 09/10/2025 | false | false | 10/31/2025 | Tharana P.A.S it21822094 |  |  | Green
xHcp4RXXD0CkBV9Klt6DWckAAAK2 | Implement Route Optimization module with dynamic re-routing (TSP + A*) | Development | Completed | Important | Palihena P.D.M.P it21079672 | Tharana P.A.S it21822094 | 10/31/2025 | 05/01/2025 | 07/31/2025 | false | false | 10/31/2025 | Palihena P.D.M.P it21079672 |  |  | Red
yf3-pD2a5EqrurL5MQS3fMkAM9RA | Define performance metrics (accuracy, MAPE, efficiency, CBM utilization) | Analysis/Software requirements | Completed | Medium | Palihena P.D.M.P it21079672;Abeydeera A.A.A.S it21822780 | Tharana P.A.S it21822094 | 10/31/2025 | 01/01/2025 | 02/28/2025 | false | false | 10/31/2025 | Palihena P.D.M.P it21079672 |  |  | Green

## Plan name
Plan name | Optimized Warehouse Management System Leveraging Industry 4.0 Technologies
Plan ID | opcdIqdPV0quSNA02wP7iMkACqqS
Date of export | 11/01/2025